## Action Items
ID | Assignee | Task | Priority | Status | Due Date | Category | Related OS | Notes
1 | SD (Satyam) | Finalize Quality OS v1.7 spec with updated P01/P17 parameters | High | In Progress | 2026-03-18 | System Design | Quality OS | Waiting on Product feedback on evaluation window
2 | SD (Satyam) | Review and resolve all pending amendments in #system-design-reboot | High | Not Started | 2026-03-25 | System Design | All
3 | Mukul | Complete parameter registry - every parameter must have value + rationale | High | In Progress | 2026-03-20 | System Design | SPR | Using SPR v1.1 + Amendment v1.4 as base
4 | Mukul | Tech language translation of Enforcement OS spec | Medium | Not Started | 2026-03-22 | System Design | Enforcement OS
5 | Devender | Validate buildability of D&A routing logic with engineering | High | Not Started | 2026-03-17 | System Design | D&A OS | Needs meeting with Marut
6 | Devender | Map event bus requirements across all 20 OSes | Medium | Not Started | 2026-03-24 | System Design | All
7 | Dhruv | Fill all parameters with real business values (not defaults) | High | In Progress | 2026-03-20 | Product | SPR | Currently at ~60% completion
8 | Dhruv | Business logic vs system logic gap analysis | High | Not Started | 2026-03-25 | Product | All
9 | Vaibhav | Product audit - validate Compensation OS against ground reality | Medium | Not Started | 2026-03-22 | Product | Compensation OS | Check bonus tiers match field economics
10 | Vaibhav | Submit amendment suggestions where system logic diverges from reality | Medium | Not Started | 2026-03-26 | Product | All
11 | Ashish | Design partner dashboard screens based on Visibility OS | High | Not Started | 2026-03-20 | Design | Visibility OS
12 | Ashish | Design internal dossier view (ops team view) | High | Not Started | 2026-03-24 | Design | Visibility OS | Refer to Ops View in simulation for reference
13 | Vikash | Build design system and component library for partner app | Medium | Not Started | 2026-03-22 | Design | All
14 | Marut | Scaffold backend services per OS architecture | High | Not Started | 2026-03-18 | Engineering | All | Dev start target: March 7
15 | Marut | Define GitHub process and branching strategy | Medium | Not Started | 2026-03-14 | Engineering | All
16 | Marut | Assign 1 FE engineer to Design Layer | High | Not Started | 2026-03-13 | Engineering | All | Blocking design team

## Goals
Goal | Owner | Target Date | Status | Details
All 20 OS specifications finalized | SD (Satyam) | 2026-03-31 | In Progress | Complete logic, parameters, edge cases for every OS
Parameter registry locked | Mukul | 2026-03-31 | In Progress | Every parameter has value, rationale, and owner
All parameters filled with real business values | Dhruv | 2026-03-31 | In Progress | Not defaults - real field-validated numbers
Partner dashboard screens designed | Ashish | 2026-03-31 | Not Started | Based on Visibility OS specs
Backend services scaffolded | Marut | 2026-03-31 | Not Started | Per OS architecture - event bus + service boundaries
Tech language translation complete | Devender | 2026-03-31 | Not Started | Specs readable and buildable by engineering